Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 27 August 2026 |
| --- | --- |
| Project Name | Employee Raise Issue |
| Maximum Marks | 5 Marks |

### Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Employee Registration & Login | USN-1 | As an employee, I can register for the application by entering my name, employee ID, email, password, and other required details. | 3 | High | Project Team |
| Sprint-1 | Employee Registration & Login | USN-2 | As an employee, I can log into the application using my employee ID/email and password. | 2 | High | Project Team |
| Sprint-1 | Raise an Issue | USN-3 | As an employee, I can raise a new issue by selecting an issue category and entering the issue description. | 3 | High | Project Team |
| Sprint-2 | Raise an Issue | USN-4 | As an employee, I can attach supporting documents or images while raising an issue. | 2 | Medium | Project Team |
| Sprint-2 | Issue Management | USN-5 | As an employee, I can view the issues that I have previously raised. | 2 | High | Project Team |
| Sprint-2 | Issue Management | USN-6 | As an employee, I can track the current status of my raised issue. | 3 | High | Project Team |
| Sprint-3 | Notifications & Communication | USN-7 | As an employee, I can receive notifications when the status of my issue is updated. | 2 | Medium | Project Team |
| Sprint-3 | Notifications & Communication | USN-8 | As an employee, I can view comments and resolution details provided for my issue. | 2 | Medium | Project Team |
| Sprint-1 | Issue Management | USN-9 | As an HR/Admin, I can view all issues raised by employees. | 3 | High | Project Team |
| Sprint-2 | Issue Assignment & Resolution | USN-10 | As an HR/Admin, I can review an employee issue and assign it to the concerned department or staff member. | 3 | High | Project Team |
| Sprint-2 | Issue Assignment & Resolution | USN-11 | As an HR/Admin, I can update the status of an issue and add comments or resolution details. | 3 | High | Project Team |
| Sprint-2 | Issue Assignment & Resolution | USN-12 | As assigned staff, I can view the issues assigned to me and work on them. | 3 | High | Project Team |
| Sprint-3 | Issue Assignment & Resolution | USN-13 | As assigned staff, I can provide resolution details and update the issue status. | 3 | High | Project Team |
| Sprint-3 | Dashboard & Reports | USN-14 | As an HR/Admin, I can view a dashboard containing pending, assigned, in-progress, and resolved issues. | 3 | Medium | Project Team |
| Sprint-3 | Dashboard & Reports | USN-15 | As an HR/Admin, I can filter issues by category, department, priority, and status. | 2 | Low | Project Team |

# Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 11 | 6 Days | 07 Sep 2026 | 12 Sep 2026 | 11 | 12 Sep 2026 |
| Sprint-2 | 16 | 6 Days | 14 Sep 2026 | 19 Sep 2026 | 16 | 19 Sep 2026 |
| Sprint-3 | 12 | 6 Days | 21 Sep 2026 | 26 Sep 2026 | 12 | 26 Sep 2026 |

### Velocity:

Imagine we have a 6-day sprint duration, and the story points completed by the team are different in each sprint. The team's velocity can be calculated as the number of story points completed per sprint.

Sprint-1 Velocity = 11 Story Points

Sprint-2 Velocity = 16 Story Points

Sprint-3 Velocity = 12 Story Points

Average Velocity (AV):

AV=11+16+123AV = \frac{11 + 16 + 12}{3} AV=339​=13

# Burndown Chart Data

You can use this data to create the burndown chart in Word/Excel:

| Sprint | Starting Story Points | Completed Story Points | Remaining Story Points |
| --- | --- | --- | --- |
| Sprint-1 | 39 | 11 | 28 |
| Sprint-2 | 28 | 16 | 12 |
| Sprint-3 | 12 | 12 | 0 |

### Burndown Progress

39 → 28 → 12 → 0

### Reference:

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/?utm_source=chatgpt.com

https://www.atlassian.com/agile/tutorials/burndown-charts?utm_source=chatgpt.com

https://www.atlassian.com/agile/project-management?utm_source=chatgpt.com

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software?utm_source=chatgpt.com

https://www.atlassian.com/agile/tutorials/epics?utm_source=chatgpt.com

https://www.atlassian.com/agile/tutorials/sprints?utm_source=chatgpt.com

https://www.atlassian.com/agile/project-management/estimation?utm_source=chatgpt.com